## Sheet1
TEAM 1
| Date | Roshan |  | Sangram |  | Abhishek chaudhari |  | Neha |  | Shubhada |  | Abhishek gawande
|  | Assigned Work | Status | Assigned Work | Status | Assigned Work | Status | Assigned Work | Status | Assigned Work | Status | Assigned Work | Status
| 2023-02-13 | 1. Project plannig, Flowchart,POJOs | Completed | 1. Project plannig, Flowchart,POJOs | Completed | 1. Project plannig, Flowchart,POJOs | Completed | 1. Project plannig, Flowchart,POJOs | Completed | 1. Project plannig, Flowchart,POJOs | Completed | 1. Project plannig, Flowchart,POJOs | Completed
1
| 2023-02-14 | 1. Routing and Designing | Completed | 1..Working on EMI model | Completed | 1.Working on defulter class and user class | Completed | crating POJO class and creating angular components | Completed | 1crating POJO class and creating angular components | Completed | Working on CB model | Completed
1
| 2023-02-15 | 1. fron tend models routing and designing | Completed | 1..Working on EMI model and emi logic work | Completed | 1.Sanction letter and email sending work | workin | working on re model and doing crud opeations | Completed | 1.enquery and details ceud and cibil score | Completed | Workking on front end pages | Completed
2023-02-16 | 1. front end and crud opertaion, designing | Completed | 1..Working defaulter model and emi logic work | Completed | 1.Sanction letter and working defaulter model | workin | working on re model and API creation and appllication form dsign | Completed | 1 designing front pages and creating api of Cb model as per requirment | Completed | EMI Logic part and Workking on front end pages | Completed